## Hoja1
Project ID | 1 |  |  | Project lifetime |  | 1 week
Client Name | Álvaro Vargas |  |  | Target Date |  | 2026-05-29
Project name | Cockpit Buildig |  |  | Last Update |  | 2026-05-26
Last Update | 2026-05-26 |  |  | Completion Date |  | 2026-05-29
Week | Milestone | Task | Task description | Status | Client feedback | Retry required | Weekly progress | Overall progress
1 | Local Development Environment (Vite + VS Code) | Install Visual Studio Code | Download and Install VS Code. Verify that it opens correctly and can create/edit project files. | Achieved |  |  | 16.67% | 3.333%
1 | Local Development Environment (Vite + VS Code) | Install Node.JS | Download and Install Node.JS. Verify instllation from terminal using version commands. | Achieved |  |  | 16.67% | 3.333%
1 | Local Development Environment (Vite + VS Code) | Install Vite | Create a local Vite Project and understand how Vite serves a webpage locally | Achieved |  |  | 16.67% | 3.333%
1 | Local Development Environment (Vite + VS Code) | First Local Render | Open he Local Vite URL and verify that changes in code immediately appear in the browser. | Achieved |  |  | 16.67% | 3.333%
1 | Local Development Environment (Vite + VS Code) | Import Figma Structure | Import the Figma-generated project structure into the local Vite environment and resolve required dependencies for successful rendering. | Achieved |  |  | 16.67% | 3.333%
1 | Local Development Environment (Vite + VS Code) | Validate Figma → Vite Render | Confirm the workflow: Figma Export → VS Code → Vite → Browser, ensuring UI changes render correctly in real time. | Achieved |  |  | 16.67% | 3.333%
2 | Frontend Foundations (Github + Figma) | Repo CleanUp | Audit current Figma-generated structure and identify required files versus temporery assets. | Achieved |  |  | 20% | 4%
2 | Frontend Foundations (Github + Figma) | Reacty Entry Point | Create and validate the application startup chain (index.html → main.tsx → app.tsx) | Achieved |  |  | 20% | 4%
2 | Frontend Foundations (Github + Figma) | Component Mapping | Identify the purpose of every major TSX component and document dependencies | Achieved |  |  | 20% | 4%
2 | Frontend Foundations (Github + Figma) | UI optimization | Consolidate duplicated components while preserving visual functionality | Achieved |  |  | 20% | 4%
2 | Frontend Foundations (Github + Figma) | GitHub Pages validation | Publish the first visible version of Cockpit online | Achieved |  |  | 20% | 4%
3 | Data Model & Excel Integration | Excel Template Design | Define the tandard spreadsheets structure for projects, milestones, tasks, progress, status, and client feedback | Achieved |  |  | 16.67% | 3.333%
3 | Data Model & Excel Integration | Template Export System | Allow users to download the official Cockpit spreadsheet template from the plaform | Achieved |  |  | 16.67% | 3.333%
3 | Data Model & Excel Integration | Excel Import Validtion | Upload and validate completed spreadsheets before processing project data. | Achieved |  |  | 16.67% | 3.333%
3 | Data Model & Excel Integration | Data Mapping Engine | Trasform spreadsheet rows into structured Cockpit project records and dashboard entitites. | Working on |  |  | 0% | 0%
3 | Data Model & Excel Integration | Dynamic Dashoard Binding | Replace static dashboards values with imported projects data, percentages and statuses. | Not yet |  |  | 0% | 0%
3 | Data Model & Excel Integration | Multi-Project Validation | Verify that different completed templates generate correct dashboards without core modifications. | Not yet |  |  | 0% | 0%
4 | Backend & API | Render Environment Setup | Create and configure a Render deployment environment for backend services. | Not yet |  |  | 0% | 0%
4 | Backend & API | FastAPI Project Creation | Build the first FastAPI backend capable of receiving project requests | Not yet |  |  | 0% | 0%
4 | Backend & API | Supabase Setup | Create and configure the project database, authentication and API access | Not yet |  |  | 0% | 0%
4 | Backend & API | Database Archiitecture | Define tables and relationships for clients, projects, milestones, tasks and feedback | Not yet |  |  | 0% | 0%
4 | Backend & API | Front-Backend Communication | Connect Cockpit frontend to FastAPI and Supabase endpoints. | Not yet |  |  | 0% | 0%
4 | Backend & API | API Validation & Deployment | Verify data exchange, persistence and backend perationafter deployment | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | Multi-Client Dashboard Generation | Geneate independient dashboards fro the same platform using imported projects daaatasets. | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | Role management | Create Administrator and client access models with appropiate permissions. | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | Progress Tracking Automation | Automatically calculate milestone completion, project progress percentages and status indicators based on imported project data and client updates. | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | PDF Reporting | Automatically update dashboard progress, milestone completion and status indicators. | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | Email Automation | Enable clients to submit feedback and synchronize updates across the platform. | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | Scalability Valdiation | Generate project reports and notify stakeholders when milestones change status. | Not yet |  |  | 0% | 0%
5 | Automation & Advanced Features | Production Release | Verify scalability and readiness for real client usage before launch. | Not yet |  |  | 0% | 0%